## Stories by Sprint
Release Name | Sprint | Start Date | End Date | Story ID | Description | Story Points | Spill Over | Total SP | Delivered
SDS | 18 | 13/3/2017 | 24/3/2017 | ICP-4913 | Code Merge from release to Dev branch | 5 |  | 33 | 33
|  |  |  | ICP-4885 | Switiching between SDS and training mode | 5
|  |  |  | ICP-4886 | Code refactoring of SDS app to group all configuration to a class | 5
|  |  |  | ICP-4909 | SDS device to load the application (SatNav) | 5
|  |  |  | ICP-4828 | SDS training mode needs a way to exit before trip complete | 5
|  |  |  | ICP-4870 | SDS - POC - Copilot for ROI | 8
SDS | 19 | 27/3/2017 | 2017-07-04 | ICP-5041 | Removal of Duplicate Codes | 8 |  | 36 | 31
|  |  |  | ICP-5042 | Remove or Modification of unused codes in SDS | 5
|  |  |  | ICP-5043 | Lombok Implementation | 5
|  |  |  | ICP-5044 | Code Refactoring | 5 | 5
|  |  |  | ICP-5045 | Code Refactoring for Trip overview fragment | 5
|  |  |  | ICP-5053 | Butter Knife Implementation | 8
SDS | 20 | 2017-10-04 | 21/4/2017 | ICP-5044 | Code Refactoring | 5 |  | 33 | 25
|  |  |  | ICP-5238 | Data Binding for Trip Overview | 5
|  |  |  | ICP-5239 | Data Binding for Delivery Overview | 5
|  |  |  | ICP-5241 | App Send time to service on the time zone | 5
|  |  |  | ICP-5246 | Data binding for Non-grocery Product list & Rejections | 5
|  |  |  | ICP-5136 | SDS Goldenpath Scenario Automation | 8 | 8
Trunking | 0 | 2017-08-05 | 19/5/2017 |  | Trunking Sprint 0 Activity
Trunking | 1 | 22/5/2017 | 2017-02-06 |  | Trunking Sprint 0 Activity Spill over

## Team Capacity
Project | Sprint | Team Member | Sprint Days | Public Holiday | Planned Vacation | Sick/Unplanned leave | Hrs/Day | Planned Availability | Actual Availabiliry | Comments | Total Planned Availability | Spare Capacity | Final Available HRS | Total Actual Availability with Spare Capacity | FTE
SDS 13/03/2017 - 24/03/2017 | Sprint 18 | Senthil | 9 |  | 1 |  | 3 | 24 | 24 |  | 288 | 57.6 | 230.4 | 288 | 5.6
|  | Likith | 9 |  |  |  | 6 | 54 | 54
|  | Madhuri | 9 |  |  |  | 0 | 0 | 0 | [7 empty] | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 0 | Sprint 1
|  | Sharada | 9 |  |  |  | 6 | 54 | 54 | [6 empty] | Total Planned Availability | 288 | 207 | 204
|  | Pawan | 9 |  |  |  | 6 | 54 | 54 | [6 empty] | Final Available HRS | 230.4 | 165.6 | 163.6
|  | Mahibub | 9 |  |  |  | 6 | 54 | 54 | [6 empty] | Spare Capacity | 57.6 | 41.4 | 40.8
|  | Narayana | 9 |  | 1 |  | 6 | 48 | 48
SDS 27/03/2017 - 07/04/2017 | Sprint 19 | Senthil | 9 | 1 |  |  | 3 | 24 | 24 |  | 207 | 41.4 | 165.6 | 207 | 5.6
|  | Likith | 9 | 1 | 1 |  | 3 | 21 | 21
|  | Madhuri | 9 | 1 |  |  | 0 | 0 | 0
|  | Sharada | 9 | 1 |  |  | 3 | 24 | 24
|  | Pawan | 9 | 1 | 1 |  | 6 | 42 | 42
|  | Mahibub | 9 | 1 |  |  | 6 | 48 | 48
|  | Narayana | 9 | 1 |  |  | 6 | 48 | 48
SDS 10/04/2017 - 21/04/2017 | Sprint 20 | Senthil | 9 |  |  |  | 3 | 27 | 27 |  | 204 | 40.8 | 163.2 | 204 | 5.6
|  | Likith | 9 |  | 1 |  | 3 | 24 | 24
|  | Madhuri | 9 |  |  |  | 0 | 0 | 0
|  | Sharada | 9 |  |  |  | 3 | 27 | 27
|  | Pawan | 9 |  | 1 |  | 6 | 48 | 48
|  | Mahibub | 9 |  | 5 |  | 6 | 24 | 24
|  | Narayana | 9 |  |  |  | 6 | 54 | 54
7

## Leave Planner
Name | Sep_2016 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | Oct_2016 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Nov_2016 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | Dec_2016 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Jan_2017 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 2017-02-01 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 2017-03-17 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 2017-04-17 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 2017-05-17 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 2017-06-17 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Saravanan Susairaj | [5 empty] | Ganesha Chaturti | [6 empty] | L | [28 empty] | L | Vijaya Dashami | [19 empty] | Deepavali |  | Kannada Rajyotsava | L | L | L | [49 empty] | L |  |  | L | [31 empty] | Republic day | [63 empty] | UGADI | [34 empty] | May Day
Senthil Sivanath | [6 empty] | L | L | L | L | [31 empty] | L
Likith | [41 empty] | L | [35 empty] | L | L | L | L | L
Madhuri | [41 empty] | L | [6 empty] | WFH | L | WFH
Narayana | [41 empty] | L | [57 empty] | L | L | L | L | L
Sharada
Maibub | [72 empty] | L | L | L |  |  | L
Pawan | [6 empty] | L | [34 empty] | L
[27 empty] | Run Rota | [72 empty] | Run Rota
H - Holiday
L - Leave
No Leaves please
Working From Home
Run Rota

## Consolidated Chart
Sprint Start Date | 2017-03-13 | 2017-03-27 | 2017-04-10 | 2017-05-08 | 2017-05-22
FTE | 5.6 | 5.6 | 5.6 | 5.6 | 5.6
Sprint Start Date | 13-Mar-17 5.6 | 27-Mar-17 5.6 | 10-Apr-17 5.6 | 08-May-17 5.6 | 22-May-17 5.6 | 00-Jan-00 | 00-Jan-00 | 00-Jan-00 | 00-Jan-00 | 00-Jan-00 | 00-Jan-00 | 00-Jan-00
Planned SP(inluding spilled over) | 33 | 36 | 33 | 21 | 21
Achived SP | 33 | 31 | 25 | 13
Average Velocity | 25.5
| Sprint 18 | Sprint 19 | Sprint 20 | Sprint 0 | Sprint 1
Total Planned Availability | 288 | 207 | 204
Final Available HRS | 230.4 | 165.6 | 163.6
Spare Capacity | 57.6 | 41.4 | 40.8

## Depicts dates & FTE's
Team Member | Individual Velocity
Senthil | 8
Likith | 5
Madhuri | 8
Maibub | 8
Narayana | 8
Sharada | 3